## Sheet1
Date	02/03/2017
TeleHealth IoT Gateway Tentative work plan

No.	Task Name	Optional	Task Discription	Name	Bhavik				Sandip				Deep				Dhruv				Milee				Vijay				Smit
					Planed Start Date	Actual Start Date	Planed End Date	Actual End Date	Planed Start Date	Actual Start Date	Planed End Date	Actual End Date	Planed Start Date	Actual Start Date	Planed End Date	Actual End Date	Planed Start Date	Actual Start Date	Planed End Date	Actual End Date	Planed Start Date	Actual Start Date	Planed End Date	Actual End Date	Planed Start Date	Actual Start Date	Planed End Date	Actual End Date	Planed Start Date	Actual Start Date	Planed End Date	Actual End Date
1	Rpi setup		Raspberry pi setup like install os and xampp	Vijay, Sandip
2	Database Design		Make Different table for data entry.	Deep, Bhavik
3	Login script patient		Authentication for patient login request.	Milee, Dhruv
4	Forgot Password (patient)		Need support incase of forgot password request.	Sandip, Bhavik
5	Registration script (patient)		Authentication for patient registration request.	Milee, Deep
6	Data collection script		Get sensor data from patient end with encryption.	Bhavik, smit
7	PHP encryption		Provide data encryption when requested at gateway.	Sandip, Vijay, Deep
8	PHP decryption		Provide data decryption when requested at gateway.	Milee, Dhruv, Smit
9	Android encryption		Provide data encryption when requested at patient mobile application.	Deep, Bhavik, Vijay
10	Android decryption		Provide data decryption when requested at patient mobile application.	Dhruv, Deep, Smit
11	PHP Web services		Binding all script for security and easyness.	Sandip, Remain
12	Notification redirection		Provide popup at doctor end.	Dhruv, Vijay, Sandip, Milee
13	Prescription Storing		Script to store doctor prescription.	Smit, Bhavik, Deep, Milee